## Risk Register
Risk ID | Asset | Threat | Vulnerability | Likelihood (1–5) | Impact (1–5) | Risk Score | Existing Control | Risk Treatment | Owner | Target Date | Status | Risk Level
R1 | AML Database | Data breach | Weak access control | 4 | 5 | 20 | Password policy | Implement MFA & RBAC | IT Security | 2026-04-30 | Open | High
R2 | Payment Application | Malware infection | Unpatched OS | 3 | 4 | 12 | Antivirus | Patch management | IT Operations | 2026-05-15 | Open | Medium
R3 | Vendor API | Data leakage | No security clause | 3 | 4 | 12 | NDA | Add vendor SLA | Legal | 2026-05-10 | Open | Medium
R4 | Employee Laptop | Theft | No disk encryption | 3 | 3 | 9 | Login password | Enable full disk encryption | IT Support | 2026-05-20 | Open | Medium
R5 | Cloud Server | DDoS attack | No WAF | 2 | 4 | 8 | Firewall | Implement WAF | Cloud Admin | 2026-05-25 | Open | Medium
R6 | Customer Data | Unauthorized access | Excessive privileges | 3 | 5 | 15 | RBAC | Privilege review | IT Security | 2026-06-05 | Open | High
R7 | Email System | Phishing | Lack of awareness | 4 | 3 | 12 | Spam filter | Awareness training | HR | 2026-06-01 | Open | Medium
R8 | Backup System | Data loss | No regular testing | 2 | 4 | 8 | Daily backup | Backup testing | IT Ops | 2026-06-10 | Open | Medium