## Findings Register
Finding ID | Type (NC/OFI) | Area | Description | ISO Ref | Severity | Evidence Gap | Owner | Due Date | Status
F-01 | OFI | Risk Treatment | RTP missing approval/sign-off | Clause 6.1 | Low | No approval field | Self | 2026-05-25 | Open
F-02 | NC | Vendor Risk | Vendor assessment checklist not defined | Annex A | Medium | No checklist file | Self | 2026-06-05 | Open
F-03 | OFI | Incident Response | No tabletop drill record | Annex A | Low | No drill evidence | Self | 2026-06-10 | Open