## Risk Treatment Plan
Risk ID | Asset | Risk Description | Treatment Option | Control to be Implemented | Responsible Owner | Target Date | Residual Risk Level | Status
R1 | AML Database | Data breach due to weak access control | Mitigate | Implement MFA and RBAC | IT Security | 30-04-2026 | Medium | Open
R2 | Payment Application | Malware due to unpatched OS | Mitigate | Automated patch management | IT Operations | 15-05-2026 | Low | Open
R3 | Vendor API | Data leakage from vendor | Transfer | Vendor SLA and security clauses | Legal | 10-05-2026 | Medium | Open
R4 | Employee Laptop | Theft without encryption | Mitigate | Enable full disk encryption | IT Support | 20-05-2026 | Low | Open
R5 | Cloud Server | DDoS attack | Mitigate | Deploy Web Application Firewall | Cloud Admin | 25-05-2026 | Medium | Open
R6 | Customer Data | Unauthorized access | Mitigate | Privilege review and logging | IT Security | 05-06-2026 | Medium | Open
R7 | Email System | Phishing attacks | Mitigate | Security awareness training | HR | 01-06-2026 | Low | Open
R8 | Backup System | Data loss | Mitigate | Periodic backup testing | IT Ops | 10-06-2026 | Low | Open